## Document Registry
Document_ID | Title | File_Path | Type | Version | Effective_Date
NET-FW-MBF-001 | Netier Master Baseline Framework | Netier_Master_Baseline_Framework.md | Framework | 1.0 | 2026-03-26
NET-FW-TCF-001 | Netier Technical Configuration Framework | Netier_Technical_Configurations.md | Framework | 1.0 | 2026-03-26
— | Production-Readiness Review: 4 Operational Deliverables | Production_Readiness_Review_2026-03-25.md | QA | 1.0 | 2026-03-26
NET-COMP-IS18-001 | IS18 Compliance Mapping — Netier MSP | IS18_Compliance_Mapping.md | Compliance | 1.0 | 2026-03-26
NET-OPS-CW-001 | ConnectWise Manage -- Security SLA Workflows & Configuration Guide | ConnectWise_SLA_Workflows.md | Compliance | 1.0 | 2026-03-26
NET-EV-ORG-001 | Organisation Context — Netier Pty Ltd | compliance-evidence/organisation-context.md | Evidence | 1.0 | 2026-03-26
NET-EV-GAP-001 | Known Gaps Register | compliance-evidence/known-gaps-register.md | Evidence | 1.0 | 2026-03-26
NET-TPL-RTR-001 | Amortized Transformation - Email Templates | Templates/Right_to_Refuse_Email_Templates.md | Template | 1.0 | 2026-03-26
NET-TPL-CRS-001 | Netier Compliance Readiness Scorecard | Templates/Compliance_Readiness_Scorecard.md | Template | 1.0 | 2026-03-26
NET-BL-M365-001 | M365 & Entra ID Security Baseline | baselines/M365_EntraID_Baseline.md | Baseline | 1.0 | 2026-03-26
NET-BL-EP-001 | Endpoint & Server Security Baseline | baselines/Endpoint_Server_Baseline.md | Baseline | 1.0 | 2026-03-26
NET-BL-NET-001 | Network Perimeter & Infrastructure Baseline | baselines/Network_Perimeter_Baseline.md | Baseline | 1.0 | 2026-03-26
NET-BL-EMAIL-001 | Email Security, Web Posture & Deliverability Baseline | baselines/Email_Web_Deliverability_Baseline.md | Baseline | 1.0 | 2026-03-26
NET-BL-OPS-001 | Operational Policies & Governing Plans | baselines/Operational_Plans_Baseline.md | Baseline | 1.0 | 2026-03-26
NET-SOP-INFRA-001 | SOP: Infrastructure & Compute Hardening | SOPs/SOP_Infrastructure_Compute.md | SOP | 1.0 | 2026-03-26
NET-SOP-IDM-001 | Standard Operating Procedures: Identity, Conditional Access & Cloud Workspace Security | SOPs/SOP_Identity_Cloud_Workspaces.md | SOP | 1.0 | 2026-03-26
NET-SOP-EP-001 | SOP: Endpoint Protection & Control | SOPs/SOP_Endpoint_Protection.md | SOP | 1.0 | 2026-03-26
NET-SOP-VULN-001 | SOP: Vulnerability Management | SOPs/SOP_Vulnerability_Management.md | SOP | 1.0 | 2026-03-26
NET-SOP-SAT-001 | SOP: Security Awareness & Training | SOPs/SOP_Security_Awareness.md | SOP | 1.0 | 2026-03-26
NET-SOP-MDM-001 | SOP: Endpoint Management (MDM/UEM) | SOPs/SOP_Endpoint_Management_MDM.md | SOP | 1.0 | 2026-03-26
NET-SOP-NET-001 | SOP: Networking & Perimeter | SOPs/SOP_Networking_Perimeter.md | SOP | 1.0 | 2026-03-26
NET-SOP-BDR-001 | SOP: Backup & Disaster Recovery | SOPs/SOP_Backup_DR.md | SOP | 1.0 | 2026-03-26
NET-SOP-RMM-001 | SOP: Remote Monitoring & Management (NinjaOne) | SOPs/SOP_RMM_NinjaOne.md | SOP | 1.0 | 2026-03-26
NET-SOP-KM-001 | SOP: Knowledge Management & Documentation | SOPs/SOP_Knowledge_Management.md | SOP | 1.0 | 2026-03-26
NET-OP-IRP-001 | Incident Response Plan (IRP) | operational-plans/Incident_Response_Plan_IRP.md | Operational Plan | 1.0 | 2026-03-26
NET-OP-BCP-001 | Business Continuity Plan (BCP) | operational-plans/Business_Continuity_Plan_BCP.md | Operational Plan | 1.0 | 2026-03-26
NET-OP-DRP-001 | Disaster Recovery Plan (DRP) | operational-plans/Disaster_Recovery_Plan_DRP.md | Operational Plan | 1.0 | 2026-03-26

## ISM Controls
ISM_Control_ID | Baseline_Document | Baseline_DocID
ISM-1173 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-0974 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1401 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1872 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1682 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1919 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1546 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1504 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1680 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-0428 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1403 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1380 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1833 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1620 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1939 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1685 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1795 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1954 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1406 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1914 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1409 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1745 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-0843 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1490 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1657 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1544 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1488 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1234 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1502 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1601 | M365 & Entra ID Security Baseline | NET-BL-M365-001
ISM-1926 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1827 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1620 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1685 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-0383 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-0843 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1490 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1656 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1657 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1544 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1143 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-0298 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1696 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1877 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1694 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1341 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1034 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1417 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1601 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-0582 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1055 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1603 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1962 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1686 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1861 | Endpoint & Server Security Baseline | NET-BL-EP-001
ISM-1528 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0631 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1192 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1427 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1028 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1181 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1577 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1182 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0385 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0520 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1321 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1332 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0534 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1304 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1800 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1963 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0518 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1782 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0619 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0705 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-1781 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0469 | Network Perimeter & Infrastructure Baseline | NET-BL-NET-001
ISM-0264 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-0569 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-0572 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1589 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-0574 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1183 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1151 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-0861 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1026 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1540 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1799 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1234 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1502 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-0963 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-0958 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1862 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1431 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1139 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1369 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1372 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1448 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1453 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1581 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-1438 | Email Security, Web Posture & Deliverability Baseline | NET-BL-EMAIL-001
ISM-0576 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1784 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-0125 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-0123 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-0140 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1437 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1579 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1580 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1431 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1547 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1548 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1511 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1515 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1708 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1631 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1452 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1568 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-1569 | Operational Policies & Governing Plans | NET-BL-OPS-001
ISM-0072 | Operational Policies & Governing Plans | NET-BL-OPS-001

## Remediation Status
Finding ID | Source | Framework(s) | Finding Title | Description | Risk | Priority | Remediation Action | Owner | Target Date | Status | Dependencies | Related Control IDs
REM-01 | Gemini R2 | ISO 27001 (all 93) | SoA Evidence Decay | Base SoA has generic evidence ('Employee Information Security Policy') and Sept 2023 review dates. Will not pass rigorous audit. | High | P1 | Rewrite SoA evidence column using soa-evidence-rewrite.csv. Reference specific tools (ThreatLocker, Intune policy IDs, CW tickets). Update all review dates. | Compliance | 2026-04-30 | In Progress (CSV generated) | None | GAP-16
REM-02 | Gemini R2 | CIS 1.1 / SOCI / NIST ID.AM | Active Network Discovery Blindspot | Agent-only visibility (NinjaOne/ThreatLocker). No scanning for unmanaged/IoT/OT devices. Attackers can map internal subnets unseen. Fatal for CI clients. | Critical | P1 | Deploy active network discovery tool (runZero or NinjaOne network discovery). Reconcile ARP tables against agent database. Prioritise CAG environment (CCTV, Gallagher, building systems). | Engineering | 2026-06-30 | Not Started | Budget approval | GAP-17 / CIS-01
REM-03 | Gemini R2 | CPS 234 / PCI DSS / SOCI | Shared Responsibility Matrix Missing | No clear delineation of Netier vs Client controls. Required for regulatory audits. Service desk cannot determine who is responsible during incidents. | High | P1 | Shared responsibility matrix created (56 controls). Attach to all new and renewed client MSAs. Brief service desk on matrix. | Governance | 2026-06-30 | In Progress (CSV generated) | Legal review of MSA attachment | GAP-19
REM-04 | Gemini R2 | SOCI / APRA / NDB / PSPF | Incident Reporting Timeline Collision | Multiple statutory timelines (12hr/20hr/72hr/30d) not unified. Risk of statutory breach during active incident. | High | P1 | Incident reporting matrix created (15 scenarios). Integrate into CW Sec-Ops board as triage checklist. Train service desk on framework-specific triggers. | Cyber Security | 2026-04-30 | In Progress (CSV generated) | IR playbook update | GAP-20
REM-05 | Internal | SOCI Act 2018 | SOCI Act CIRMP for CAG | No formal Critical Infrastructure Risk Management Program documented for Canberra Airport. Legislative non-compliance risk. | Critical | P1 | Draft CIRMP covering cyber/personnel/supply chain/physical. Map existing ISO 27001 controls. Establish board-level CI governance with CAG. Engage legal. | Cyber Security / Management | 2026-06-30 | Not Started | Legal consultation; CAG management engagement | SOCI-CIRMP-01
REM-06 | Internal | ISM Dec 2025 | AI Governance — No Formal Policy | No AI usage policy despite active Claude/Copilot usage internally and on client endpoints. ISM Dec 2025 mandatory requirement. | High | P2 | Draft AI Usage Policy. Create system cards for knowledge-db AI components. Establish AI tool approval process integrated with ThreatLocker. | Cyber Security | 2026-06-30 | Not Started | None | ISM-AI-01 / ISM-AI-02
REM-07 | Internal | ISM Dec 2025 | Cryptographic Bill of Materials | No CBOM process. NinjaOne software inventory doesn't include crypto dependency analysis. | High | P2 | By 2026-09-30: complete evaluation of CycloneDX BOM crypto extensions vs IBM CBOM Utility. By 2026-12-31: generate CBOM for top 10 critical software packages (identified from NinjaOne software inventory) and publish to shared compliance repository. See Netier Compliance Engine roadmap Phase 5. | Cyber Security | 2026-12-31 | Not Started | Netier Compliance Engine Phase 5 development | ISM-CBOM-01
REM-08 | Internal | E8 ML2-ML3 / ISM / CIS 6 | Privileged Access — PAW/JIT Partial | Azure AD PIM deployed at CAG (CW #1752374 MFA Setup PIM Accounts; #1752093 CAG PIM Account - Nathan Sole; weekly PIM digests #1754981). PAWs not yet deployed. PIM not rolled out beyond CAG. | High | P2 | Extend PIM rollout from CAG to all managed tenants. Establish PAW program for DC/AAD/security tool administration. Enforce phishing-resistant MFA on all admin accounts. | Cyber Security | 2026-09-30 | In Progress (CAG PIM live) | Entra ID P2 licensing for remaining tenants | E8-RAP
REM-09 | Internal | E8 ML3 / ISM-AUTH-01 | Phishing-Resistant MFA — Operational (Expanding) | FIDO2 keys actively deployed — CW tickets for broken keys (#1746812) PIN issues (#1745815) sign-in errors (#1714723) key-at-home (#1735004). NinjaOne FIDO compatibility issue tracked (#1748363). Confluence KB exists: netier.atlassian.net/wiki/spaces/STS/FIDO2. Not pilot — operational for subset of staff. Gap: not universal across all clients/users. | Medium | P2 | Expand FIDO2 deployment to all admin accounts across all clients. Migrate ML3 clients from push to passkey/FIDO2. Track adoption rate via Netier Compliance Engine Phase 3 (Entra Graph API sweep). | Cyber Security | 2026-09-30 | In Progress (operational for staff) | FIDO2 key procurement for remaining users | E8-MFA
REM-10 | Gemini R2 | E8 ML3 / SOC 2 CC7 / NIST DE | No SIEM — Centralised Log Correlation | No SIEM deployed. ThreatLocker blocks not correlated with Entra ID failed logins. Defense Evasion = Red in ATT&CK. | High | P2 | Evaluate SIEM (Microsoft Sentinel, Wazuh, Elastic). Centralise logging from ThreatLocker + Entra ID + Sophos + NinjaOne. Track MTTD/MTTR metrics. | Cyber Security | 2026-12-31 | Not Started | Budget approval; licensing | GAP-18 / CSF-DE-01
REM-11 | Internal | Privacy Act / APPs / NDB | NDB Not Integrated in IR | NDB assessment criteria not in IR playbook. No OAIC notification template. No formal process for notifying affected individuals. | High | P1 | Integrate NDB criteria into IR playbook. Create OAIC notification template. Designate NDB assessment role. Run tabletop exercise. | Cyber Security | 2026-06-30 | Not Started | IR playbook update (REM-04) | PRIV-NDB-01
REM-12 | Internal | ISO A.6.3 / ISM / IS18 PR4 / CIS 14 | Security Awareness Training Platform | uSecure procured (deployment in progress). CyberCred Security Champions deployed at cyber.netier.team. SOP written: NET-SOP-SAT-001. Phishing simulations to be configured in uSecure. | Medium | P2 | Complete uSecure deployment and configure monthly phishing simulations. Integrate uSecure completion data with CyberCred points system. Document onboarding security induction per NET-SOP-SAT-001. | Cyber Security | 2026-06-30 | In Progress | uSecure deployment scheduling | IS18-AWARE-01
REM-13 | Internal | E8 ML3 / ISO A.5.29-30 / SOC 2 A1 | DR Testing Not Regular | Full environment restoration testing not performed regularly. DR SLAs not documented per client. | Medium | P2 | By 2026-05-31: schedule and execute first full VM restoration test for one Enterprise-tier client (CAG preferred). Document: time to restore, integrity verification result, delta from stated RTO. By 2026-06-30: formalise quarterly cadence in CW recurring activities. Verify immutable backup configs. Document per-client RTO/RPO in agreements. | Cyber Security | 2026-06-30 | Not Started | Client agreement updates | E8-RB / CSF-RC-01
REM-14 | Gemini R2 | PSPF / DISP | Data Sovereignty — US-Based Vendors | NinjaOne and ThreatLocker are US-based. Telemetry/metadata sent to US servers. Partial awareness evidenced: CW #1666677 'MITRE Data Location 365' (M365 residency investigated); CW #1743025 'Check Wi-Fi classification for defence clients' (active defence classification work). Formal PSPF/DISP data sovereignty assessment not completed. | Medium | P2 | By 2026-05-15: send DPA request to NinjaOne and ThreatLocker legal departments. By 2026-06-30: receive and review DPAs. By 2026-09-30: produce data sovereignty risk assessment memo for management sign-off. Build on existing M365 data residency work (#1666677). | Management | 2026-09-30 | In Progress (awareness exists) | Legal consultation | GAP-21
REM-15 | Internal | ISM-AUTH-01 | SSPR Security Questions Still Enabled | Some M365 tenants may still permit security questions as SSPR verification method. ISM explicitly prohibits this. | Medium | P2 | Audit all managed M365 tenants for SSPR configurations. Disable security questions. Remove email OTP from permitted methods. | Cyber Security | 2026-06-30 | Not Started | Tenant access via GDAP | ISM-AUTH-01
REM-16 | Gemini R2 | MITRE ATT&CK (Exfiltration) | No Explicit DLP | No Data Loss Prevention solution deployed. Missing protections against mass exfiltration to unauthorized cloud storage. | Medium | P3 | By 2026-09-30: identify 3 highest-risk clients by PII volume. By 2026-12-31: deploy Purview DLP in audit mode for those 3 clients. Q1 2027: review findings and move to enforcement. Requires M365 E5 licensing assessment first. | Cyber Security | 2026-12-31 | Not Started | M365 E5 licensing assessment | GAP-22
REM-17 | Gemini R2 | MITRE ATT&CK (Persistence) / PCI | No File Integrity Monitoring | No FIM capability. Silent persistence possible despite baseline hardening. PCI DSS requires FIM for CDE systems. | Medium | P3 | FIM deployment dependent on SIEM selection (REM-10). Once SIEM chosen: deploy FIM agents to Tier 1 critical servers (CAG DCs, file servers) within 30 days. Expand to all managed servers within 90 days. Prioritise PCI-scoped systems. | Cyber Security | 2026-12-31 | Not Started | SIEM deployment (REM-10) | GAP-23
REM-18 | Gemini R2 | CSF GV.SC / SOCI | Supply Chain Concentration Risk | Complete reliance on Big 4 vendors (Microsoft, Sophos, NinjaOne, ThreatLocker). Systemic kill-switch risk if one is compromised. | Medium | P2 | By 2026-06-30: create ISO 27036-aligned vendor risk assessment template. By 2026-09-30: complete assessments for Microsoft, Sophos, NinjaOne, ThreatLocker. Document blast radius and break-glass procedures per vendor. Store in compliance repository. | Cyber Security | 2026-09-30 | Not Started | None | GAP-24 / CSF-GV-02
REM-19 | Internal | IS18 PR5 | IS18 Annual Return Not Standardised | 169-requirement checklist not mapped to tooling. Evidence collection manual. Annual return process depends on ad-hoc effort. | Medium | P2 | By 2026-04-30: contact QLD GCISO office or QLD Digital to obtain current IS18 annual return template and guidance. By 2026-06-30: complete requirement-to-evidence-source mapping for all 169 requirements. By 2026-09-30: automate via Netier Compliance Engine Phase 4. | Cyber Security | 2026-09-30 | Not Started | Netier Compliance Engine Phase 4 development | IS18-ATT-01
REM-20 | Internal | APRA CPS 234 / PCI DSS / ISM | No Systematic Penetration Testing | No independent penetration testing program. No ASV scans. Netier Compliance Engine covers external web/email/DNS but not comprehensive pen testing. | Medium | P2 | By 2026-06-30: obtain 3 quotes from CyberCX, Secureworks, or equivalent PCI QSA-certified providers. Scope: external infrastructure + 1 internal segment (CAG). By 2026-09-30: complete first annual pen test. Establish annual cadence. Quarterly ASV scans for PCI-scoped clients. | Cyber Security | 2026-09-30 | Not Started | Budget; vendor selection | CPS234-TEST-01 / PCI-REQ11
REM-21 | Internal | ISO 9001 Clause 10 | No Continual Improvement Register | No formal improvement register. Improvements identified ad-hoc. No systematic tracking. Critical for ISO 9001. | High | P2 | By 2026-04-30: create improvement register as CW Configuration item or shared tracker. Seed with existing findings from Gemini reviews, audit non-conformities, and incident PIRs. Present at next management review. Define ongoing sources: audits, incidents, client feedback, compliance reviews. | Management | 2026-06-30 | Not Started | None | QMS-IMPROVE
REM-22 | Internal | PSPF (all pillars) | PSPF Not Formally Mapped | Federal government clients require PSPF compliance. Not formally mapped. Personnel/physical/governance gaps. | Medium | P2 | By 2026-06-30: map existing controls to PSPF Policies 1-16 (current version as of March 2026). Use Netier Compliance Engine's 10 PSPF controls as starting point. Identify gaps in Personnel (AGSVA clearance management) and Physical (office security). Create PSPF compliance template for federal engagements. | Management | 2026-09-30 | Not Started | None | PSPF-GOV-01 through PSPF-INVEST-01
REM-23 | Internal | APRA CPS 234 | APRA CPS 234 Not Assessed | Financial clients subject to APRA regulation. No gap analysis performed. No capability statement for APRA clients. | Medium | P2 | By 2026-04-30: review CW client list for APRA-regulated entities (banks, insurers, super funds). If zero found: document and deprioritise. If found: complete CPS 234 gap analysis by 2026-09-30. Create capability statement leveraging ISO certification. | Cyber Security | 2026-12-31 | Not Started | Client list review | CPS234-INFO-01 through CPS234-3P-01
REM-24 | Internal | PCI DSS v4.0 | PCI DSS Scope Not Determined | Clients handling card data but CDE boundaries not identified. No segmentation assessment. No ASV scans. | Medium | P3 | By 2026-04-30: review CW client list for PCI-scoped entities (card data handlers). If zero found: document and deprioritise. If found: map CDE boundaries by 2026-06-30. Engage ASV by 2026-09-30. Assess firewall rules against PCI Req 1. | Cyber Security | 2026-12-31 | Not Started | Client identification | PCI-REQ1 through PCI-REQ11
REM-25 | Gemini R2 | NIST CSF 2.0 GV | Govern Function Missing | NIST CSF 2.0 Govern function (risk strategy, supply chain risk, organisational context) has no ISO Annex A equivalent. Not documented. | Low | P3 | By 2026-09-30: draft risk management strategy document covering risk appetite statement, organisational context, and supply chain governance. Present to management for endorsement at next quarterly review. Ensure risk appetite documented and communicated. | Management | 2026-12-31 | Not Started | None | CSF-GV-01 / CSF-GV-02
REM-26 | Internal | DISP (H1R) | DISP Obligations Not Formally Mapped | GAP-10: DISP member obligations not mapped to existing controls. Personnel security and facility clearances not formalised. | Medium | P2 | By 2026-06-30: map existing controls to DISP H1R obligations (personnel security, facility security, ICT security, governance). Identify gaps in AGSVA clearance management and secure facilities. By 2026-09-30: create DISP compliance template for defence engagements. | Management | 2026-09-30 | Not Started | None | DISP-PERS-01 through DISP-ICT-01

## SOP Coverage
TCF_Section | Domain | SOP_Document_ID | SOP_File | Status
1.0 | Infrastructure & Compute | NET-SOP-INFRA-001 | SOPs/SOP_Infrastructure_Compute.md | COMPLETE
2.0 | Identity & Cloud Workspaces | NET-SOP-IDM-001 | SOPs/SOP_Identity_Cloud_Workspaces.md | COMPLETE
3.0 | Endpoint Protection & Control | NET-SOP-EP-001 | SOPs/SOP_Endpoint_Protection.md | COMPLETE
4.0 | Vulnerability Management | NET-SOP-VULN-001 | SOPs/SOP_Vulnerability_Management.md | COMPLETE
5.0 | Security Awareness & Training | NET-SOP-SAT-001 | SOPs/SOP_Security_Awareness.md | COMPLETE
6.0 | Endpoint Management (MDM / UEM) | NET-SOP-MDM-001 | SOPs/SOP_Endpoint_Management_MDM.md | COMPLETE
7.0 | Networking & Perimeter | NET-SOP-NET-001 | SOPs/SOP_Networking_Perimeter.md | COMPLETE
8.0 | Backup & Disaster Recovery | NET-SOP-BDR-001 | SOPs/SOP_Backup_DR.md | COMPLETE
9.0 | Remote Monitoring & Management (RMM) | NET-SOP-RMM-001 | SOPs/SOP_RMM_NinjaOne.md | COMPLETE
10.0 | Knowledge Management & Documentation | NET-SOP-KM-001 | SOPs/SOP_Knowledge_Management.md | COMPLETE

## Tool Stack
Category | Tool or Document | Purpose | Frameworks Addressed | Deployment Scope | Evidence Location | Notes
Endpoint Protection | Sophos MDR (Managed Detection & Response) | Endpoint detection and response with 24/7 SOC monitoring | ISO A.8.7, E8 (multiple), ISM, CIS 10, NIST PR.PT, SOC2-CC7 | All managed clients — workstations and servers | Sophos Central console; CW tickets for threat alerts | Sophos MDR provides both endpoint AV and managed threat hunting
Endpoint Protection | ThreatLocker | Application control, elevation management, ringfencing, storage control | E8-AC (ML1-ML3), ISO A.8.19, ISM, CIS 2 | All managed clients — deployed across CAG/STS/Optiva/Zen/MITRE/HAM/SENTCON | ThreatLocker Unified Audit portal; ConnectWise Manage tickets for app/elevation requests (e.g. #1755124) | Core E8 application control tool — blocks unapproved executables
RMM & Patching | NinjaOne | Remote monitoring and management, patch deployment, software inventory, backup monitoring | E8-PA, E8-POS, ISO A.8.8, A.8.9, ISM, CIS 7 | All managed clients | NinjaOne Administration portal; patch policies (E8 ML1/ML2/ML3); SOFTWARE_PATCH_MANAGEMENT activities | Policies named per E8 maturity level — good audit evidence
Identity & Access | Microsoft Entra ID (Azure AD) | Identity provider, conditional access, MFA, SSPR, PIM (planned) | E8-MFA, E8-RAP, ISO A.5.15-18, A.8.5, ISM, PSPF-PERS, CIS 6, NIST PR.AC | All M365 clients | Entra admin center; Conditional Access policy exports (e.g. ECL policies in OneDrive) | GDAP used for delegated admin across client tenants
Identity & Access | Conditional Access Policies | Enforce MFA, block legacy auth, location-based access, device compliance | E8-MFA, ISO A.8.5, ISM-AUTH-01, NIST PR.AC | All M365 clients | Entra ID > Conditional Access; OneDrive exports (ECL/CAG/MITRE policies) | Key evidence for MFA and authentication controls
Identity & Access | FIDO2 Security Keys (Operational) | Phishing-resistant MFA for staff and admin accounts | E8-MFA ML3, ISM-AUTH-01, NIST PR.AC | Operational — Netier staff and select client admin accounts | Entra ID authentication methods policy; CW tickets #1746812 (broken key), #1745815 (PIN issues), #1714723 (sign-in errors), #1735004 (key-at-home); Confluence KB: netier.atlassian.net/wiki/spaces/STS/FIDO2 | Gap: not universal across all clients/users — expanding per REM-09
Email Security | Sophos Email Gateway | Email filtering and anti-phishing | ISO A.8.23, ISM-EMAIL-01, CIS 9 | Clients using Sophos email | Sophos Central; CW phishing alert tickets (e.g. #1755111) | Supplements M365 Exchange Online Protection
Email Security | SPF/DKIM/DMARC | Email authentication to prevent spoofing | ISM-EMAIL-01 (ISM-0574, ISM-1151, ISM-0269, ISM-1540, ISM-1799), ISO A.5.14 | All managed domains | DNS records; Netier Compliance Engine ISM scanner results | Some domains may still be DMARC p=none — gap identified
Email Security | MTA-STS / TLS-RPT | Enforce TLS for mail transport and report failures | ISM-EMAIL-01 (ISM-1589, ISM-1590, ISM-1026) | Partial — not all client domains | DNS records; _mta-sts subdomain configs | Gap: not universally deployed
Network Security | WatchGuard Firewalls | Perimeter firewall and VPN | ISO A.8.20-22, PCI-REQ1, CIS 13, NIST PR.AC | Multiple client sites | WatchGuard Cloud / local management; firewall rule exports | Primary firewall vendor for most clients
Network Security | FortiGate Firewalls | Perimeter firewall (select sites) | ISO A.8.20-22, PCI-REQ1, CIS 13 | Select clients (e.g. CAG-AVN-FW) | FortiGate management console; Slack vuln alerts (2026-01-13) | Secondary firewall vendor — CAG aviation network
Network Security | Cloudflare DNS / Tunnels | DNS management and secure tunnelling | ISM-DNS-01, ISO A.8.20, CIS 9 | Select client domains | Cloudflare Zero Trust dashboard (dash.cloudflare.com) | DNSSEC available but not enabled on all domains — gap identified
Network Security | CrowdSec | Collaborative intrusion prevention | ISO A.8.16, NIST DE.CM | Internal infrastructure (docker host) | CrowdSec console / docker logs | Internal use — not deployed across client environments
Backup & DR | Veeam Backup & Replication | VM and server backup with monitoring | E8-RB, ISO A.5.29-30, A.8.13, SOC2-A1, CIS 11 | All clients with on-premises servers | Veeam console; CW auto-created backup alert tickets (e.g. #1754921) | Gap: full restoration testing not regular; immutable backup verification not automated
Backup & DR | NinjaOne Backup | Cloud and local backup via NinjaOne agent | E8-RB, ISO A.8.13 | Select clients | NinjaOne backup policies | Supplement to Veeam for endpoints and smaller environments
Monitoring & Logging | Grafana + Prometheus | Metrics dashboards and alerting | ISO A.8.15-16, NIST DE.CM, SOC2-CC7, CIS 8 | Internal infrastructure | Grafana + Prometheus dashboards (grafana.internal on docker-host CT100) | Internal monitoring — not deployed across all client environments
Monitoring & Logging | Uptime Kuma | Service availability monitoring | ISO A.8.14, SOC2-A1 | Internal and select client services | Uptime Kuma status dashboard (hosted on docker-host CT100) | Monitors service availability and response times
Monitoring & Logging | NinjaOne (Network Monitoring) | Agent-based network and endpoint monitoring | ISO A.8.15, CIS 1, NIST DE.CM | All managed clients | NinjaOne Network Monitor dashboard (app.ninjarmm.com) | Network device discovery and performance monitoring via NinjaOne agents
ITSM | ConnectWise Manage | Ticketing, time tracking, agreements, client management, incident/change/problem management | ISO A.5.24-28, ITIL (all processes), SOC2-CC8, CIS 17 | All clients — central service delivery platform | ConnectWise Manage portal (manage.netier.com.au); ticket history; agreement records | Core ITSM platform — all incidents/changes/problems tracked here
Documentation | OneDrive (Netier / Client folders) | Policy documents and project evidence | All frameworks (evidence repository) | Netier-wide | OneDrive folder structure per client | Contains policy docs (CSCC Patch Management | Data Backup | Security Baselines etc.)
Documentation | BookStack | Internal documentation wiki | ISO A.5.37, A.7.5 (ISO 9001) | Internal | BookStack instance on docker host | Knowledge base for procedures and runbooks
Vulnerability Management | Netier Compliance Engine ISM Scanner | Custom ISM compliance scanner — TLS, email auth, DNS, web security headers | ISM-EMAIL-01, ISM-WEB-01, ISM-DNS-01, ISM-CRYPTO-01, OWASP | Client domains | Netier Compliance Engine scan results; ism.ts framework definitions | Custom-built tool scanning against specific ISM control requirements
Vulnerability Management | CIS Benchmarks | Hardening standards for Windows/M365/browsers | CIS Controls (all), ISO A.8.9, E8-UAH | Multiple clients — Intune security baselines | OneDrive: CIS benchmark PDFs; Intune baseline exports (MITRE/ILABS/MOB/CFT/CONP) | CIS Benchmark policies deployed via Intune
Security Awareness | uSecure | Security awareness training and phishing simulation platform | ISO A.6.3, ISM, IS18 PR4, CIS 14, NIST PR.AT | All managed clients | uSecure admin console (app.usecure.io); phishing simulation reports | Procured — deployment in progress
Security Awareness | CyberCred Security Champions | Points-based gamification platform for security culture and training incentives | ISO A.6.3, ISM, IS18 PR4, CIS 14 | Netier internal (extending to managed clients) | CyberCred platform (cyber.netier.team); leaderboard; completion reports | Deployed — tracks training completion and phishing simulation performance with reward tiers
Application Hardening | Intune Security Baselines | Windows/M365/Defender security baselines, macro hardening, browser restrictions | E8-UAH, E8-CMM, ISO A.8.9, CIS 4 | M365-managed clients | Microsoft Intune admin center (intune.microsoft.com); OneDrive backup exports (MITRE JSON configs) | Includes macro restrictions and Office hardening policies
Application Hardening | WDAC / AppLocker | Windows Defender Application Control policies | E8-AC ML3, ISO A.8.19 | In progress — not universally deployed | Intune WDAC policies | Gap: Microsoft recommended block rules not universally applied
Encryption | BitLocker | Full disk encryption for Windows endpoints | ISO A.8.24, ISM, PCI-REQ3, NIST PR.DS | All managed Windows workstations | Intune compliance policies; Entra ID BitLocker key recovery | Enforced via Intune compliance policies
Encryption | TLS 1.2+ Enforcement | Transport encryption for all web services | ISM-CRYPTO-01 (ISM-1139, ISM-1369, ISM-1372), PCI-REQ4 | All client web services | Netier Compliance Engine scanner results; Intune cipher suite restrictions | Gap: some legacy systems may still use TLS 1.0/1.1
Physical Security | Client-managed | Physical security of client premises and data centres | ISO A.7.1-14, PSPF-PHYS, DISP-PHYS, PCI-REQ9 | Client responsibility — Netier advises | Client physical security documentation | Netier office has access control; client physical security is client-owned
Policy Library | Information Security Policy | Overarching ISMS policy | ISO A.5.1, all frameworks | Netier-wide | OneDrive: ISMS Policy folder | Core policy underpinning all controls
Policy Library | Acceptable Use Policy | Acceptable use of IT resources | ISO A.5.10, ISM, CIS 14 | Netier-wide + clients | OneDrive | Standard policy expected by all frameworks
Policy Library | Data Backup Policy (Draft) | Backup strategy and requirements | E8-RB, ISO A.8.13, SOC2-A1 | Netier-wide | OneDrive: Data Backup Policy - Draft.docx | Status: Draft — needs finalisation
Policy Library | CSCC Patch Management Policy | Patch management procedures aligned to E8 | E8-PA, E8-POS, ISO A.8.8 | Netier-wide | OneDrive: CSCC Patch Management Policy.docx | Covers patching cadence per E8 maturity level
Policy Library | IS18 Information Security Policy | QLD government IS18 compliance policy | IS18 (all requirements) | QLD government clients | OneDrive: STARS governance docs | Template for QLD government client compliance